Single-Case Action Plan

November, 2020 – April, 2021

This action plan is based on the observations conducted at Kardan Schools and on key areas for improvement as identified in discussions with the Managing Director and other Senior Staff.

The action points were also reflected on the School Strategic Improvement Plan to ensure proper follow-up. The SIP is a live document that is updated and revised throughout the academic year.

Key Priorities:

- Improving the teaching staff provision across all schools

- Streamlining academic and administrative processes

- Increasing student enrollment

- Improving the provision for teaching and learning

C: Completed

P: In Progress

O: Ongoing

OT: On Target

AR: At Risk

NS: Not Started

| Priority 1: Improving the teaching staff provision across all schools |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Targeted Objective (1): Conducting Evaluations of teaching staff |  |  |  |  |  |
| Strategies to be employed Key actions to achieve the objective – What? | Success criteria How is the success for the targeted objective measured? | Review of success | In charge | Resources | Timescales |
| - Research appropriate objective evaluation criteria in the context of the current Kardan Schools stage of development - Develop a 4-scale rubric for each selected criteria - Digitalize the rubric in Google forms once finalized and approved - Present evaluation criteria and rubric to Senior Leaders - Disseminate evaluation criteria and rubric to teachers through Senior Leaders - Create an observation schedule for each school - Conduct lesson observations for all teaching staff - Summarize results and report to Managing Director (MD) to feed back into firing/retention/promotion procedure | - Coherent and consistent lesson observation framework is developed and disseminated to all stakeholders - Each teacher has been observed a minimum of 1 time for at least ½ a lesson - Teachers who are drastically underperforming are invited for discussion and provided a chance for a second observation | - Evidenced observations have been conducted for all teachers - Summary reports are presented to the MD | - DE - SLT | - Observation rubric - Observation schedule - Results summary report | - Nov, 20 |
| Targeted Objective (2): Firing/retention/promotion/hiring of staff |  |  |  |  |  |
| Strategies to be employed Key actions to achieve the objective – What? | Success criteria How is the success for the targeted objective measured? | Review of success | In charge | Resources | Timescales |
| - Conduct post-evaluation Senior staff decision meeting on firing/retention/promotion - Re-organize school structures - Review teacher salaries, teaching load, and allocations - Advertise open positions - Conduct interviews and finalize hiring process - Organize induction training for new teachers | - Lists for firing/retention/promotion/hiring are compiled - Exit interviews are held with all staff members to be fired - Ads for new positions are posted and CVs are collected in files by subject - Induction schedule is created and circulated to all involved | - Exit interviews - All positions have been filled - Organizational structure has been revised | - MD - DE - SLT - HR | - Advertising budget - Organizational Structure - Induction schedule | - Dec, 20 |
| Priority 2: Streamlining academic and administrative processes |  |  |  |  |  |
| Targeted Objective (1): Developing and implementing academic and administrative policies and procedures |  |  |  |  |  |
| Strategies to be employed Key actions to achieve the objective – What? | Success criteria How is the success for the targeted objective measured? | Review of success | In charge | Resources | Timescales |
| - Outline all school administrative and academic processes - Develop comprehensive policies to regulate each process - Develop comprehensive Standard Operating Procedures (SOPs) to guide each process - Introduce all new policies, processes, and procedures to staff - Prepare a comprehensive staff handbook, containing all school regulatory documents - Establish school governing bodies – a Local Advisory Board (LAB), Parent Council, and Student Council for all Kradan Schools - Introduce all new policies to the school governing bodies - Develop a system for monitoring of policy and SOP implementation | - All school processes have been identified and a policy and SOPs have been written and disseminated to all stakeholders - Governing bodies are operational and involved in school life - All policies are fully integrated in the school life | - Comprehensive guiding documentation - Governing bodies MoM - Monitoring SOP | - MD - DE - SLT - HR - FM | - Staff handbook | - Dec, 20 - Mar, 21 |
| Targeted Objective (2): Budgeting and procurement for AY 2021 |  |  |  |  |  |
| Strategies to be employed Key actions to achieve the objective – What? | Success criteria How is the success for the targeted objective measured? | Review of success | In charge | Resources | Timescales |
| - Develop a comprehensive list of materials, including IT, books, teaching aids, office supplies, furniture, building upgrades, other CAPEX - Develop a comprehensive list of all OPEX expenses, including salaries, utilities, office supplies, petrol, transport, security etc. - Create procurement wish lists by department and school - Finalize annual school budgets - Implement central inventory system - Procure CAPEX and set forth an annual monthly plan for OPEX | - Budgets are submitted prior to the beginning of the academic year - The majority of procurement is completed prior to the beginning of the academic year - Central inventory is established and operational - OPEX expenses are planned out | - Facilities upgrades - Finalized CAPEX procurement - OPEX planning - Inventory planning | - MD - DE - FM - SLT - AM | - Budget wish lists - Finances - OPEX calendar - KGS contract - Inventory system - Storage space | - Feb, 20 |
| Targeted Objective (3): Academic and administrative planning for AY 2021 |  |  |  |  |  |
| Strategies to be employed Key actions to achieve the objective – What? | Success criteria How is the success for the targeted objective measured? | Review of success | In charge | Resources | Timescales |
| - Develop School Improvement Plan (SIP) - Introduce action planning to Senior Leadership Team (SLT) - Develop SLT action plans - Review and finalize SLT action plans - Develop Middle Leaders action plans - Review and finalize Middle Leaders action plans - Develop teacher action plans - Review and finalize teacher action plans - Introduce a system for continuous action plan monitoring and evaluation | - Action plans are created, reviewed and implemented | - Action plan implementation and follow-up | - MD - DE - SLT - Admin | - Action plan template - PD | - Jan, 20 |
| Priority 3: Increasing student enrollment |  |  |  |  |  |
| Targeted Objective (1): Conducting media campaigns |  |  |  |  |  |
| Strategies to be employed Key actions to achieve the objective – What? | Success criteria How is the success for the targeted objective measured? | Review of success | In charge | Resources | Timescales |
| - Develop central Kardan Schools website and professional emails - Develop individual section websites - Deploy SEO to guarantee top search results - Develop Social Media campaign, involving students and parents - Explore potential relationships with Afghan influencers | - Website is live - Google search yields top results - Social media campaign shows high engagement with over 60% positive response | - SEO measures - Social media campaign measures | - MD - DE - CO | - Graphic Design - Website design - Finances - SEO specialist | - Jan, 20 |
| Targeted Objective (2): Improving community relationships |  |  |  |  |  |
| Strategies to be employed Key actions to achieve the objective – What? | Success criteria How is the success for the targeted objective measured? | Review of success | In charge | Resources | Timescales |
| - Develop and implement a positive attendance reinforcement discount scheme for parents - Develop community outreach programs - Introduce referral discount system - Introduce large/extended family discount system - Introduce entrance assessments and interviews | - 70% increase in inquiries and 50% increase in enrollments | - Number of newly enrolled students/families as per new schemes | - MD - DE - SLT - CO - Registrar | - Finances - Advertising | - Jan, 20 |
| Priority 4: Improving the provision for teaching and learning |  |  |  |  |  |
| Targeted Objective (1): Conducting teacher training |  |  |  |  |  |
| Strategies to be employed Key actions to achieve the objective – What? | Success criteria How is the success for the targeted objective measured? | Review of success | In charge | Resources | Timescales |
| - Develop a comprehensive annual Professional Development (PD) calendar - Develop a Winter break PD calendar - Introduce an annual PD budget | - Organized PD schedule - 100% improvement in demo lessons vs. November observations | - Lesson observations | - DE - SLT | - PD schedule | - Mar, 20 |
| Targeted Objective (2): Physical and academic preparations for AY 2021 |  |  |  |  |  |
| Strategies to be employed Key actions to achieve the objective – What? | Success criteria How is the success for the targeted objective measured? | Review of success | In charge | Resources | Timescales |
| - Prepare classroom environment for AY 2021 - Prepare School Climate environment for AY 2021 - Conduct teacher training on physical environment policies and procedures - Conduct Health and Safety teacher trainings - Develop academic, assessment, activities, well-being, events, and parent engagement calendars - Create school timetables, class and teacher allocations, duties schedules - Prepare booksale | - Classroom and school climate environments are following all health and safety norms and show 100% improvement from AY 2020 - Booksale is conducted and 70% of families participate | - Walkthroughs | - DE - SLT | - Teaching aids - Furniture - Building upgrades - Office supplies | - Mar, 20 |
| Targeted Objective (3): Implementing aligned curriculum model |  |  |  |  |  |
| Strategies to be employed Key actions to achieve the objective – What? | Success criteria How is the success for the targeted objective measured? | Review of success | In charge | Resources | Timescales |
| - Introduce aligned curriculum model to teachers - Conduct lesson plan trainings - Conduct curriculum alignment trainings with teachers - Develop pacing guides - Develop lesson plans for the first school month - Introduce lesson planning and review policy - Deliver mock physical and virtual lessons | - All pacing guides and lessons are planned in relation to the aligned curriculum model - All lessons for the first month of school have been thoroughly planned out | - Observations | - DE - SLT - Middle Leaders - Teachers | - Document templates - PD schedule | - Mar, 20 |
| Targeted Objective (4): Implementing an appropriate LMS/VLE/SIS |  |  |  |  |  |
| Strategies to be employed Key actions to achieve the objective – What? | Success criteria How is the success for the targeted objective measured? | Review of success | In charge | Resources | Timescales |
| - Research potential solutions available on the market - Set up demo meetings - Procure software and train teachers on using it - Set up lessons for the first month of school - Introduce to the governing bodies, as well as the wider community of parents and students | - All lessons are migrated to a central virtual system - All students and parents access the system on a daily basis | - Appropriate system is implemented | - MD - DE - SLT | - Finances - PD for teachers | - Dec, 20 |
| Targeted Objective (5): Developing effective assessment systems |  |  |  |  |  |
| Strategies to be employed Key actions to achieve the objective – What? | Success criteria How is the success for the targeted objective measured? | Review of success | In charge | Resources | Timescales |
| - Introduce MAP assessment for KIS - Introduce appropriate cognitive ability assessments (CogAT) for all schools - Align internal assessments to curriculum standards - Develop and implement a system for internal assessment review - Develop a weighted assessment scheme for summative assessments - Train teachers into the development and use of formative assessments - Develop data analysis systems - Train teachers into use of data for differentiated instruction - Introduce SEND assessments - Introduce online resources for literacy and numeracy | - All subjects conduct diagnostic assessments - External assessments are used in core subjects, and where appropriate - Assessment data is used to feed back into lesson planning - All teachers perform data-generating formative assessments at the end of each curriculum standard delivery | - Classroom observations - Lesson plans - Internal assessments - External assessments - Data | - DE - SLT - Teachers | - Finances - PD | - April, 20 |